## Overview
Credit Sense + Fiserv OLB Implementation
Relative-week project plan for client delivery
Project profile |  |  | Portfolio summary
Project | Credit Sense by SavvyMoney integration into Fiserv OLB |  | Required Tasks | Milestones |  | Stage Gates |  | Completion
Client |  |  | 231 | 19 |  | 10 |  | 0%
Current Project Week | 1
Project Manager |  |  | Blocked | At Risk |  | In Progress |  | Not Needed
Planning Horizon | 17 |  | 0 | 0 |  | 0 |  | 0
Overall Status | Not Started
Executive roadmap | Primary focus | Start | End | Gate | Stage Gate | Target | Status | Owner
Define | Scope, product, vendors, technical design, UX, and risk review | 1 | 5 | ​G1 | G1 Scope Approved | 3 | Not Started | Sponsor
Build | Fiserv and SavvyMoney configuration, SSO, navigation, and analytics | 5 | 8 | ​G2 | G2 Solution Approved | 5 | Not Started | Architecture
Prove | QA, UAT, accessibility, security validation, and defects | 7 | 11 | ​G3 | G3 Risk Approved | 6 | Not Started | Legal
Prepare | Operations, support, training, communications, and release approvals | 8 | 13 | ​G4 | G4 Build Complete | 8 | Not Started | PM
Release | Production, soft launch, general launch, and hypercare | 13 | 17 | ​G5 | G5 QA Complete | 10 | Not Started | QA
|  |  |  | ​G6 | G6 UAT Complete | 11 | Not Started | Product
|  |  |  | ​G7 | G7 Launch Ready | 13 | Not Started | Sponsor
|  |  |  | ​G8 | G8 Production Accepted | 13 | Not Started | Product
|  |  |  | ​G9 | G9 Market Ready | 14 | Not Started | Sponsor
|  |  |  | ​G10 | G10 BAU | 17 | Not Started | Sponsor
Maintenance | Update the Master Plan before the weekly meeting. Set Status to Not Needed to remove an item from the Weekly Action View and progress metrics without deleting it.
Status definitions | Use one status per item |  |  | Schedule health | Calculated from status and timing
Not Started | Work has not begun. |  |  | On Track | Starts more than two weeks ahead or remains within its planned window.
In Progress | Work is underway with an accountable owner. |  |  | Due Soon | Starts within the current week plus the next two weeks.
At Risk | Target or exit criteria may be missed; mitigation is required. |  |  | Late | Planned end week has passed and the item is not complete.
Blocked | Work cannot proceed; a decision or action is required. |  |  | At Risk | Status indicates a material threat to the plan.
Complete | Deliverable is accepted and the dependency is satisfied. |  |  | Blocked | Status indicates work cannot proceed.
Not Needed | Excluded from the Weekly Action View and progress; retained for traceability. |  |  | Schedule TBD | Start Week or End Week is missing.
Gate rule | Mark a stage gate Complete only after its exit criteria are satisfied and the approval is recorded.
Planning basis | Detailed itemized schedule from the referenced Project Schedule Integration conversation. All dates are relative project weeks.

## Weekly Action View
Weekly Action View
Active, late, at-risk, blocked, and near-term items; Not Needed and Complete items are excluded
Project Week | 1 |  | Items Requiring Attention | 70 |  | Maintenance | Edit Status, Next Action, Blocker / Decision Needed, and ownership in the Master Plan.
WBS ID | Phase / Workstream | Activity | Accountable Owner | Start Week | End Week | Status | Schedule Health | Next Action | Blocker / Decision Needed | Supporting Teams
​1.1 | Project Initiation | Confirm business sponsor | Client | 1 | 1 | Not Started | Due Soon
​1.2 | Project Initiation | Assign client project manager | Client | 1 | 1 | Not Started | Due Soon
​1.3 | Project Initiation | Assign Digital/Product lead | Client | 1 | 1 | Not Started | Due Soon
​1.4 | Project Initiation | Confirm Fiserv implementation contacts | Fiserv | 1 | 1 | Not Started | Due Soon
​1.5 | Project Initiation | Confirm SavvyMoney implementation contacts | SavvyMoney | 1 | 1 | Not Started | Due Soon
​1.6 | Project Initiation | Identify technical/integration resources | Client | 1 | 1 | Not Started | Due Soon
​1.7 | Project Initiation | Identify Security/InfoSec resources | Client | 1 | 1 | Not Started | Due Soon
​1.8 | Project Initiation | Identify Legal/Compliance resources | Client | 1 | 1 | Not Started | Due Soon
​1.9 | Project Initiation | Identify Marketing/Comms resources | Client | 1 | 1 | Not Started | Due Soon
​1.10 | Project Initiation | Identify Operations/Support resources | Client | 1 | 1 | Not Started | Due Soon
​1.11 | Project Initiation | Confirm project scope | Product | 1 | 1 | Not Started | Due Soon |  |  | PM
​1.12 | Project Initiation | Define in-scope Credit Sense capabilities | Product | 1 | 1 | Not Started | Due Soon
​1.13 | Project Initiation | Document out-of-scope capabilities | Product | 1 | 1 | Not Started | Due Soon
​1.14 | Project Initiation | Define launch target | Sponsor | 1 | 1 | Not Started | Due Soon |  |  | PM
​1.15 | Project Initiation | Define project governance | PM | 1 | 1 | Not Started | Due Soon
​1.16 | Project Initiation | Establish weekly project meeting | PM | 1 | 1 | Not Started | Due Soon
​1.17 | Project Initiation | Establish RAID log | PM | 1 | 1 | Not Started | Due Soon
​1.18 | Project Initiation | Establish decision log | PM | 1 | 1 | Not Started | Due Soon
​1.19 | Project Initiation | Establish project repository | PM | 1 | 1 | Not Started | Due Soon
​1.20 | Project Initiation | Kickoff meeting | PM | 2 | 2 | Not Started | Due Soon
​2.1 | Business & Product Definition | Define business objectives | Product | 1 | 1 | Not Started | Due Soon
​2.2 | Business & Product Definition | Define customer value proposition | Product | 1 | 1 | Not Started | Due Soon |  |  | UX
​2.3 | Business & Product Definition | Define target customer population | Product | 1 | 1 | Not Started | Due Soon
​2.4 | Business & Product Definition | Confirm eligibility requirements | Product | 2 | 2 | Not Started | Due Soon |  |  | Compliance
​2.5 | Business & Product Definition | Define first-release capabilities | Product | 2 | 2 | Not Started | Due Soon
​2.6 | Business & Product Definition | Confirm whether offers are included | Product | 2 | 2 | Not Started | Due Soon |  |  | Marketing
​2.7 | Business & Product Definition | Define web experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX
​2.8 | Business & Product Definition | Define mobile experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX
​2.9 | Business & Product Definition | Define enrollment experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX
​2.10 | Business & Product Definition | Define returning-user experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX
​2.11 | Business & Product Definition | Define servicing/support experience | Product | 2 | 2 | Not Started | Due Soon |  |  | Ops
​2.12 | Business & Product Definition | Define success KPIs | Product | 2 | 2 | Not Started | Due Soon |  |  | Data
​2.13 | Business & Product Definition | Establish baseline metrics | Data | 3 | 3 | Not Started | Due Soon
​2.14 | Business & Product Definition | Finalize product requirements | Product | 3 | 3 | Not Started | Due Soon
​3.1 | Vendor / Contract Readiness | Confirm SavvyMoney contract | Procurement | 1 | 1 | Not Started | Due Soon
​3.2 | Vendor / Contract Readiness | Confirm licensed capabilities | Procurement | 1 | 1 | Not Started | Due Soon |  |  | Product
​3.3 | Vendor / Contract Readiness | Review Fiserv dependencies | PM | 1 | 1 | Not Started | Due Soon |  |  | Technology
​3.4 | Vendor / Contract Readiness | Confirm implementation fees | Procurement | 2 | 2 | Not Started | Due Soon
​3.5 | Vendor / Contract Readiness | Confirm production/support SLAs | Vendor Mgmt | 2 | 2 | Not Started | Due Soon
​3.6 | Vendor / Contract Readiness | Confirm data responsibilities | Security | 2 | 2 | Not Started | Due Soon |  |  | Legal
​3.7 | Vendor / Contract Readiness | Complete vendor risk review | Vendor Mgmt | 3 | 3 | Not Started | Due Soon
​4.1 | Technical Discovery | Document current Fiserv OLB environment | Client Tech | 2 | 2 | Not Started | Due Soon
​4.2 | Technical Discovery | Confirm Fiserv OLB version/configuration | Fiserv | 2 | 2 | Not Started | Due Soon
​4.3 | Technical Discovery | Review Credit Sense architecture | SavvyMoney | 2 | 2 | Not Started | Due Soon
​4.4 | Technical Discovery | Confirm integration method | Fiserv | 2 | 2 | Not Started | Due Soon |  |  | SavvyMoney
​4.5 | Technical Discovery | Confirm SSO method | Fiserv | 2 | 2 | Not Started | Due Soon |  |  | SavvyMoney
​4.6 | Technical Discovery | Identify customer identifiers | Client Tech | 2 | 2 | Not Started | Due Soon
​4.7 | Technical Discovery | Map required customer attributes | Client | 3 | 3 | Not Started | Due Soon |  |  | SavvyMoney
​4.8 | Technical Discovery | Document authentication flow | Architecture | 3 | 3 | Not Started | Due Soon
​4.9 | Technical Discovery | Document enrollment flow | Architecture | 3 | 3 | Not Started | Due Soon |  |  | Product
​4.10 | Technical Discovery | Document data flow | Architecture | 3 | 3 | Not Started | Due Soon
​4.11 | Technical Discovery | Confirm test environment | Fiserv | 3 | 3 | Not Started | Due Soon
​4.12 | Technical Discovery | Confirm production environment | Fiserv | 3 | 3 | Not Started | Due Soon
​4.13 | Technical Discovery | Confirm mobile integration requirements | Fiserv | 3 | 3 | Not Started | Due Soon
​4.14 | Technical Discovery | Confirm browser requirements | Tech | 3 | 3 | Not Started | Due Soon |  |  | QA
​5.1 | UX / Experience Design | Current-state journey review | UX | 2 | 2 | Not Started | Due Soon |  |  | Product
​5.2 | UX / Experience Design | Determine OLB navigation placement | UX | 2 | 2 | Not Started | Due Soon |  |  | Product
​5.3 | UX / Experience Design | Determine mobile navigation placement | UX | 2 | 2 | Not Started | Due Soon |  |  | Product
​5.4 | UX / Experience Design | Define promotional entry points | UX | 3 | 3 | Not Started | Due Soon |  |  | Marketing
​5.5 | UX / Experience Design | Define enrollment messaging | UX | 3 | 3 | Not Started | Due Soon |  |  | Content
​5.6 | UX / Experience Design | Define consent/disclosure placement | UX | 3 | 3 | Not Started | Due Soon |  |  | Compliance
​5.7 | UX / Experience Design | Define loading/error states | UX | 3 | 3 | Not Started | Due Soon
​5.8 | UX / Experience Design | Define support/error escalation experience | UX | 3 | 3 | Not Started | Due Soon |  |  | Ops
​6.1 | Legal / Compliance / Privacy | Provide solution overview | Product | 2 | 2 | Not Started | Due Soon
​6.3 | Legal / Compliance / Privacy | Review customer consent | Compliance | 3 | 3 | Not Started | Due Soon
​6.4 | Legal / Compliance / Privacy | Review disclosures | Compliance | 3 | 3 | Not Started | Due Soon
​6.5 | Legal / Compliance / Privacy | Review FCRA implications | Compliance | 3 | 3 | Not Started | Due Soon |  |  | Legal
​6.6 | Legal / Compliance / Privacy | Review Reg V implications | Compliance | 3 | 3 | Not Started | Due Soon
​6.7 | Legal / Compliance / Privacy | Review privacy notice implications | Privacy | 3 | 3 | Not Started | Due Soon
​G1 | Stage Gates | G1 Scope Approved | Sponsor | 3 | 3 | Not Started | Due Soon |  |  | Product

## Master Plan
Master Project Plan
Credit Sense by SavvyMoney integration into Fiserv OLB
Manage accountability, timing, status, next actions, and decisions here. Not Needed items are excluded from the Weekly Action View and progress metrics.
WBS ID | Phase / Workstream | Activity | Accountable Owner | Start Week | End Week | Status | Schedule Health | Next Action | Blocker / Decision Needed | Supporting Teams | Dependencies | Duration (Weeks) | Milestone / Stage Gate | Notes | Key
​1.1 | Project Initiation | Confirm business sponsor | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 1
​1.2 | Project Initiation | Assign client project manager | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 2
​1.3 | Project Initiation | Assign Digital/Product lead | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 3
​1.4 | Project Initiation | Confirm Fiserv implementation contacts | Fiserv | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 4
​1.5 | Project Initiation | Confirm SavvyMoney implementation contacts | SavvyMoney | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 5
​1.6 | Project Initiation | Identify technical/integration resources | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 6
​1.7 | Project Initiation | Identify Security/InfoSec resources | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 7
​1.8 | Project Initiation | Identify Legal/Compliance resources | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 8
​1.9 | Project Initiation | Identify Marketing/Comms resources | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 9
​1.10 | Project Initiation | Identify Operations/Support resources | Client | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 10
​1.11 | Project Initiation | Confirm project scope | Product | 1 | 1 | Not Started | Due Soon |  |  | PM | ​1.1–1.10 | 1 |  |  | 11
​1.12 | Project Initiation | Define in-scope Credit Sense capabilities | Product | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.11 | 1 |  |  | 12
​1.13 | Project Initiation | Document out-of-scope capabilities | Product | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.11 | 1 |  |  | 13
​1.14 | Project Initiation | Define launch target | Sponsor | 1 | 1 | Not Started | Due Soon |  |  | PM | ​1.11 | 1 |  |  | 14
​1.15 | Project Initiation | Define project governance | PM | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.1–1.10 | 1 |  |  | 15
​1.16 | Project Initiation | Establish weekly project meeting | PM | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.15 | 1 |  |  | 16
​1.17 | Project Initiation | Establish RAID log | PM | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.15 | 1 |  |  | 17
​1.18 | Project Initiation | Establish decision log | PM | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.15 | 1 |  |  | 18
​1.19 | Project Initiation | Establish project repository | PM | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.15 | 1 |  |  | 19
​1.20 | Project Initiation | Kickoff meeting | PM | 2 | 2 | Not Started | Due Soon |  |  |  | ​1.1–1.19 | 1 | Milestone |  | 20
​2.1 | Business & Product Definition | Define business objectives | Product | 1 | 1 | Not Started | Due Soon |  |  |  | ​1.11 | 1 |  |  | 21
​2.2 | Business & Product Definition | Define customer value proposition | Product | 1 | 1 | Not Started | Due Soon |  |  | UX | ​2.1 | 1 |  |  | 22
​2.3 | Business & Product Definition | Define target customer population | Product | 1 | 1 | Not Started | Due Soon |  |  |  | ​2.1 | 1 |  |  | 23
​2.4 | Business & Product Definition | Confirm eligibility requirements | Product | 2 | 2 | Not Started | Due Soon |  |  | Compliance | ​2.3 | 1 |  |  | 24
​2.5 | Business & Product Definition | Define first-release capabilities | Product | 2 | 2 | Not Started | Due Soon |  |  |  | ​2.1 | 1 |  |  | 25
​2.6 | Business & Product Definition | Confirm whether offers are included | Product | 2 | 2 | Not Started | Due Soon |  |  | Marketing | ​2.5 | 1 |  |  | 26
​2.7 | Business & Product Definition | Define web experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX | ​2.5 | 1 |  |  | 27
​2.8 | Business & Product Definition | Define mobile experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX | ​2.5 | 1 |  |  | 28
​2.9 | Business & Product Definition | Define enrollment experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX | ​2.5 | 1 |  |  | 29
​2.10 | Business & Product Definition | Define returning-user experience | Product | 2 | 2 | Not Started | Due Soon |  |  | UX | ​2.5 | 1 |  |  | 30
​2.11 | Business & Product Definition | Define servicing/support experience | Product | 2 | 2 | Not Started | Due Soon |  |  | Ops | ​2.5 | 1 |  |  | 31
​2.12 | Business & Product Definition | Define success KPIs | Product | 2 | 2 | Not Started | Due Soon |  |  | Data | ​2.1 | 1 |  |  | 32
​2.13 | Business & Product Definition | Establish baseline metrics | Data | 3 | 3 | Not Started | Due Soon |  |  |  | ​2.12 | 1 |  |  | 33
​2.14 | Business & Product Definition | Finalize product requirements | Product | 3 | 3 | Not Started | Due Soon |  |  |  | ​2.1–2.13 | 1 | Milestone |  | 34
​3.1 | Vendor / Contract Readiness | Confirm SavvyMoney contract | Procurement | 1 | 1 | Not Started | Due Soon |  |  |  | — | 1 |  |  | 35
​3.2 | Vendor / Contract Readiness | Confirm licensed capabilities | Procurement | 1 | 1 | Not Started | Due Soon |  |  | Product | ​3.1 | 1 |  |  | 36
​3.3 | Vendor / Contract Readiness | Review Fiserv dependencies | PM | 1 | 1 | Not Started | Due Soon |  |  | Technology | ​1.4 | 1 |  |  | 37
​3.4 | Vendor / Contract Readiness | Confirm implementation fees | Procurement | 2 | 2 | Not Started | Due Soon |  |  |  | ​3.1, 3.3 | 1 |  |  | 38
​3.5 | Vendor / Contract Readiness | Confirm production/support SLAs | Vendor Mgmt | 2 | 2 | Not Started | Due Soon |  |  |  | ​3.1 | 1 |  |  | 39
​3.6 | Vendor / Contract Readiness | Confirm data responsibilities | Security | 2 | 2 | Not Started | Due Soon |  |  | Legal | ​3.1 | 1 |  |  | 40
​3.7 | Vendor / Contract Readiness | Complete vendor risk review | Vendor Mgmt | 3 | 3 | Not Started | Due Soon |  |  |  | ​3.1 | 1 |  |  | 41
​3.8 | Vendor / Contract Readiness | Resolve contract gaps | Legal | 4 | 4 | Not Started | On Track |  |  | Procurement | ​3.1–3.7 | 1
​4.1 | Technical Discovery | Document current Fiserv OLB environment | Client Tech | 2 | 2 | Not Started | Due Soon |  |  |  | ​1.20 | 1 |  |  | 42
​4.2 | Technical Discovery | Confirm Fiserv OLB version/configuration | Fiserv | 2 | 2 | Not Started | Due Soon |  |  |  | ​4.1 | 1 |  |  | 43
​4.3 | Technical Discovery | Review Credit Sense architecture | SavvyMoney | 2 | 2 | Not Started | Due Soon |  |  |  | ​1.20 | 1 |  |  | 44
​4.4 | Technical Discovery | Confirm integration method | Fiserv | 2 | 2 | Not Started | Due Soon |  |  | SavvyMoney | ​4.1–4.3 | 1 |  |  | 45
​4.5 | Technical Discovery | Confirm SSO method | Fiserv | 2 | 2 | Not Started | Due Soon |  |  | SavvyMoney | ​4.4 | 1 |  |  | 46
​4.6 | Technical Discovery | Identify customer identifiers | Client Tech | 2 | 2 | Not Started | Due Soon |  |  |  | ​4.4 | 1 |  |  | 47
​4.7 | Technical Discovery | Map required customer attributes | Client | 3 | 3 | Not Started | Due Soon |  |  | SavvyMoney | ​4.6 | 1 |  |  | 48
​4.8 | Technical Discovery | Document authentication flow | Architecture | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.5 | 1 |  |  | 49
​4.9 | Technical Discovery | Document enrollment flow | Architecture | 3 | 3 | Not Started | Due Soon |  |  | Product | ​4.5 | 1 |  |  | 50
​4.10 | Technical Discovery | Document data flow | Architecture | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.7 | 1 |  |  | 51
​4.11 | Technical Discovery | Confirm test environment | Fiserv | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.4 | 1 |  |  | 52
​4.12 | Technical Discovery | Confirm production environment | Fiserv | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.4 | 1 |  |  | 53
​4.13 | Technical Discovery | Confirm mobile integration requirements | Fiserv | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.4 | 1 |  |  | 54
​4.14 | Technical Discovery | Confirm browser requirements | Tech | 3 | 3 | Not Started | Due Soon |  |  | QA | ​4.4 | 1 |  |  | 55
​4.15 | Technical Discovery | Define error-handling requirements | Architecture | 4 | 4 | Not Started | On Track |  |  |  | ​4.8–4.10 | 1
​4.16 | Technical Discovery | Complete solution design | Architecture | 4 | 4 | Not Started | On Track |  |  |  | ​4.1–4.15 | 1
​4.17 | Technical Discovery | Technical design signoff | Client | 4 | 4 | Not Started | On Track |  |  | Fiserv; SavvyMoney | ​4.16 | 1 | Milestone
​5.1 | UX / Experience Design | Current-state journey review | UX | 2 | 2 | Not Started | Due Soon |  |  | Product | ​2.14 | 1 |  |  | 56
​5.2 | UX / Experience Design | Determine OLB navigation placement | UX | 2 | 2 | Not Started | Due Soon |  |  | Product | ​5.1 | 1 |  |  | 57
​5.3 | UX / Experience Design | Determine mobile navigation placement | UX | 2 | 2 | Not Started | Due Soon |  |  | Product | ​5.1 | 1 |  |  | 58
​5.4 | UX / Experience Design | Define promotional entry points | UX | 3 | 3 | Not Started | Due Soon |  |  | Marketing | ​5.1 | 1 |  |  | 59
​5.5 | UX / Experience Design | Define enrollment messaging | UX | 3 | 3 | Not Started | Due Soon |  |  | Content | ​2.9 | 1 |  |  | 60
​5.6 | UX / Experience Design | Define consent/disclosure placement | UX | 3 | 3 | Not Started | Due Soon |  |  | Compliance | ​5.5 | 1 |  |  | 61
​5.7 | UX / Experience Design | Define loading/error states | UX | 3 | 3 | Not Started | Due Soon |  |  |  | ​4.15 | 1 |  |  | 62
​5.8 | UX / Experience Design | Define support/error escalation experience | UX | 3 | 3 | Not Started | Due Soon |  |  | Ops | ​5.7 | 1 |  |  | 63
​5.9 | UX / Experience Design | Review responsive behavior | UX | 4 | 4 | Not Started | On Track |  |  |  | ​5.2–5.8 | 1
​5.10 | UX / Experience Design | Accessibility review | UX | 4 | 4 | Not Started | On Track |  |  | Accessibility | ​5.2–5.9 | 1
​5.11 | UX / Experience Design | Stakeholder walkthrough | Product | 4 | 4 | Not Started | On Track |  |  | UX | ​5.1–5.10 | 1
​5.12 | UX / Experience Design | Incorporate feedback | UX | 5 | 5 | Not Started | On Track |  |  |  | ​5.11 | 1
​5.13 | UX / Experience Design | Final experience approval | Product | 5 | 5 | Not Started | On Track |  |  |  | ​5.12 | 1 | Milestone
​6.1 | Legal / Compliance / Privacy | Provide solution overview | Product | 2 | 2 | Not Started | Due Soon |  |  |  | ​2.14 | 1 |  |  | 64
​6.2 | Legal / Compliance / Privacy | Provide screenshots/user flows | UX | 4 | 4 | Not Started | On Track |  |  |  | ​5.11 | 1
​6.3 | Legal / Compliance / Privacy | Review customer consent | Compliance | 3 | 3 | Not Started | Due Soon |  |  |  | ​6.1 | 1 |  |  | 65
​6.4 | Legal / Compliance / Privacy | Review disclosures | Compliance | 3 | 3 | Not Started | Due Soon |  |  |  | ​6.1 | 1 |  |  | 66
​6.5 | Legal / Compliance / Privacy | Review FCRA implications | Compliance | 3 | 3 | Not Started | Due Soon |  |  | Legal | ​6.1 | 1 |  |  | 67
​6.6 | Legal / Compliance / Privacy | Review Reg V implications | Compliance | 3 | 3 | Not Started | Due Soon |  |  |  | ​6.1 | 1 |  |  | 68
​6.7 | Legal / Compliance / Privacy | Review privacy notice implications | Privacy | 3 | 3 | Not Started | Due Soon |  |  |  | ​6.1 | 1 |  |  | 69
​6.8 | Legal / Compliance / Privacy | Review data-sharing arrangement | Privacy | 4 | 4 | Not Started | On Track |  |  | Legal | ​4.10 | 1
​6.9 | Legal / Compliance / Privacy | Review marketing claims | Compliance | 4 | 4 | Not Started | On Track |  |  | Marketing | ​6.1 | 1
​6.10 | Legal / Compliance / Privacy | Review terms and conditions | Legal | 4 | 4 | Not Started | On Track |  |  |  | ​6.1 | 1
​6.11 | Legal / Compliance / Privacy | Document required changes | Compliance | 5 | 5 | Not Started | On Track |  |  |  | ​6.2–6.10 | 1
​6.12 | Legal / Compliance / Privacy | Implement required changes | Product | 5 | 5 | Not Started | On Track |  |  | UX; Tech | ​6.11 | 1
​6.13 | Legal / Compliance / Privacy | Final legal/compliance approval | Legal | 6 | 6 | Not Started | On Track |  |  | Compliance | ​6.12 | 1 | Milestone
​7.1 | Security / Risk | Architecture security review | Security | 4 | 4 | Not Started | On Track |  |  |  | ​4.16 | 1
​7.2 | Security / Risk | Review SSO/authentication | Security | 4 | 4 | Not Started | On Track |  |  |  | ​4.8 | 1
​7.3 | Security / Risk | Review data transmission | Security | 4 | 4 | Not Started | On Track |  |  |  | ​4.10 | 1
​7.4 | Security / Risk | Review data storage/retention | Security | 4 | 4 | Not Started | On Track |  |  | Privacy | ​4.10 | 1
​7.5 | Security / Risk | Review encryption requirements | Security | 4 | 4 | Not Started | On Track |  |  |  | ​4.10 | 1
​7.6 | Security / Risk | Review vendor controls | Vendor Risk | 4 | 4 | Not Started | On Track |  |  |  | ​3.7 | 1
​7.7 | Security / Risk | Confirm logging/monitoring | Security | 5 | 5 | Not Started | On Track |  |  | Tech | ​4.16 | 1
​7.8 | Security / Risk | Resolve security findings | Tech | 5 | 6 | Not Started | On Track |  |  | Vendor | ​7.1–7.7 | 2
​7.9 | Security / Risk | Security approval | Security | 6 | 6 | Not Started | On Track |  |  |  | ​7.8 | 1 | Milestone
​8.1 | Configuration / Development | Provision SavvyMoney test environment | SavvyMoney | 5 | 5 | Not Started | On Track |  |  |  | ​4.17 | 1
​8.2 | Configuration / Development | Provision Fiserv test configuration | Fiserv | 5 | 5 | Not Started | On Track |  |  |  | ​4.17 | 1
​8.3 | Configuration / Development | Configure client branding | SavvyMoney | 5 | 5 | Not Started | On Track |  |  |  | ​5.13 | 1
​8.4 | Configuration / Development | Configure SSO | Fiserv | 5 | 6 | Not Started | On Track |  |  | SavvyMoney | ​8.1–8.2 | 2
​8.5 | Configuration / Development | Configure customer attribute mapping | Vendor | 6 | 6 | Not Started | On Track |  |  | Client Tech | ​4.7 | 1
​8.6 | Configuration / Development | Configure OLB navigation | Fiserv | 6 | 6 | Not Started | On Track |  |  | Client | ​5.13 | 1
​8.7 | Configuration / Development | Configure mobile navigation | Fiserv | 6 | 6 | Not Started | On Track |  |  | Client | ​5.13 | 1
​8.8 | Configuration / Development | Configure entitlements | Fiserv | 6 | 6 | Not Started | On Track |  |  |  | ​8.2 | 1
​8.9 | Configuration / Development | Configure enrollment | SavvyMoney | 6 | 6 | Not Started | On Track |  |  |  | ​8.4–8.5 | 1
​8.10 | Configuration / Development | Configure disclosures | SavvyMoney | 6 | 6 | Not Started | On Track |  |  | Client | ​6.13 | 1
​8.11 | Configuration / Development | Configure support links | Client | 6 | 6 | Not Started | On Track |  |  | Vendor | ​5.8 | 1
​8.12 | Configuration / Development | Configure analytics tagging | Data | 7 | 7 | Not Started | On Track |  |  | Tech | ​2.12 | 1
​8.13 | Configuration / Development | Configure production monitoring | Tech | 7 | 7 | Not Started | On Track |  |  |  | ​7.7 | 1
​8.14 | Configuration / Development | Developer integration testing | Tech | 7 | 7 | Not Started | On Track |  |  | Vendor | ​8.4–8.13 | 1
​8.15 | Configuration / Development | Correct integration issues | Tech | 7 | 8 | Not Started | On Track |  |  | Vendor | ​8.14 | 2
​8.16 | Configuration / Development | Build complete | PM | 8 | 8 | Not Started | On Track |  |  | Tech | ​8.15 | 1 | Milestone
​9.1 | QA / System Testing | Create master test plan | QA | 7 | 7 | Not Started | On Track |  |  |  | ​2.14, 4.17 | 1
​9.2 | QA / System Testing | Create test accounts | QA | 7 | 7 | Not Started | On Track |  |  | Tech | ​8.1–8.2 | 1
​9.3 | QA / System Testing | Test first-time enrollment | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.4 | QA / System Testing | Test returning customer | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.5 | QA / System Testing | Test SSO | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.6 | QA / System Testing | Validate customer data mapping | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.7 | QA / System Testing | Test OLB entry point | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.8 | QA / System Testing | Test mobile entry point | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.9 | QA / System Testing | Test entitlements | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.10 | QA / System Testing | Test error scenarios | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.11 | QA / System Testing | Test session timeout behavior | QA | 8 | 8 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.12 | QA / System Testing | Browser testing | QA | 9 | 9 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.13 | QA / System Testing | Mobile/device testing | QA | 9 | 9 | Not Started | On Track |  |  |  | ​8.16 | 1
​9.14 | QA / System Testing | Accessibility testing | QA | 9 | 9 | Not Started | On Track |  |  | UX | ​8.16 | 1
​9.15 | QA / System Testing | Analytics validation | QA | 9 | 9 | Not Started | On Track |  |  | Data | ​8.12 | 1
​9.16 | QA / System Testing | Log defects | QA | 8 | 9 | Not Started | On Track |  |  |  | ​9.3–9.15 | 2
​9.17 | QA / System Testing | Defect remediation | Tech | 9 | 9 | Not Started | On Track |  |  | Vendor | ​9.16 | 1
​9.18 | QA / System Testing | Regression testing | QA | 10 | 10 | Not Started | On Track |  |  |  | ​9.17 | 1
​9.19 | QA / System Testing | QA signoff | QA | 10 | 10 | Not Started | On Track |  |  |  | ​9.18 | 1 | Milestone
​10.1 | User Acceptance Testing | Define UAT participants | Product | 9 | 9 | Not Started | On Track |  |  | PM | — | 1
​10.2 | User Acceptance Testing | Develop UAT scenarios | Product | 9 | 9 | Not Started | On Track |  |  | QA | ​9.1 | 1
​10.3 | User Acceptance Testing | Develop UAT script | Product | 9 | 9 | Not Started | On Track |  |  | QA | ​10.2 | 1
​10.4 | User Acceptance Testing | Prepare tester instructions | PM | 9 | 9 | Not Started | On Track |  |  |  | ​10.3 | 1
​10.5 | User Acceptance Testing | Prepare UAT environment | Tech | 10 | 10 | Not Started | On Track |  |  |  | ​9.19 | 1
​10.6 | User Acceptance Testing | Conduct UAT kickoff/workshop | PM | 10 | 10 | Not Started | On Track |  |  | Product | ​10.1–10.5 | 1
​10.7 | User Acceptance Testing | Business testing | UAT Team | 10 | 10 | Not Started | On Track |  |  |  | ​10.6 | 1
​10.8 | User Acceptance Testing | Branch/support testing | Operations | 10 | 10 | Not Started | On Track |  |  |  | ​10.6 | 1
​10.9 | User Acceptance Testing | Marketing testing | Marketing | 10 | 10 | Not Started | On Track |  |  |  | ​10.6 | 1
​10.10 | User Acceptance Testing | Capture defects/issues | PM | 10 | 10 | Not Started | On Track |  |  | QA | ​10.7–10.9 | 1
​10.11 | User Acceptance Testing | Remediate critical defects | Tech | 10 | 11 | Not Started | On Track |  |  | Vendor | ​10.10 | 2
​10.12 | User Acceptance Testing | UAT regression | QA | 11 | 11 | Not Started | On Track |  |  | UAT Team | ​10.11 | 1
​10.13 | User Acceptance Testing | Obtain business signoff | Product | 11 | 11 | Not Started | On Track |  |  |  | ​10.12 | 1 | Milestone
​11.1 | Operations & Support Readiness | Define customer support model | Operations | 8 | 8 | Not Started | On Track |  |  |  | ​2.11 | 1
​11.2 | Operations & Support Readiness | Define Level 1 support ownership | Operations | 8 | 8 | Not Started | On Track |  |  |  | ​11.1 | 1
​11.3 | Operations & Support Readiness | Define escalation to Digital | Operations | 8 | 8 | Not Started | On Track |  |  |  | ​11.1 | 1
​11.4 | Operations & Support Readiness | Define escalation to SavvyMoney | Operations | 8 | 8 | Not Started | On Track |  |  | Vendor | ​11.1 | 1
​11.5 | Operations & Support Readiness | Document common failure scenarios | Operations | 9 | 9 | Not Started | On Track |  |  | Product | ​9.10 | 1
​11.6 | Operations & Support Readiness | Develop call-center scripting | Operations | 10 | 10 | Not Started | On Track |  |  |  | ​11.5 | 1
​11.7 | Operations & Support Readiness | Develop branch scripting | Operations | 10 | 10 | Not Started | On Track |  |  |  | ​11.5 | 1
​11.8 | Operations & Support Readiness | Develop customer FAQ | Product | 10 | 10 | Not Started | On Track |  |  | Content | ​11.5 | 1
​11.9 | Operations & Support Readiness | Develop internal FAQ | Product | 10 | 10 | Not Started | On Track |  |  | Ops | ​11.5 | 1
​11.10 | Operations & Support Readiness | Create support documentation | Operations | 10 | 10 | Not Started | On Track |  |  |  | ​11.5 | 1
​11.11 | Operations & Support Readiness | Train contact center | Operations | 11 | 11 | Not Started | On Track |  |  |  | ​11.6–11.10 | 1
​11.12 | Operations & Support Readiness | Train branches | Operations | 11 | 11 | Not Started | On Track |  |  |  | ​11.7–11.10 | 1
​11.13 | Operations & Support Readiness | Confirm vendor support contacts | PM | 11 | 11 | Not Started | On Track |  |  |  | ​11.4 | 1
​11.14 | Operations & Support Readiness | Complete operational readiness review | PM | 12 | 12 | Not Started | On Track |  |  | Ops | ​11.1–11.13 | 1 | Milestone
​12.1 | Marketing & Communications | Define launch communication strategy | Marketing | 8 | 8 | Not Started | On Track |  |  | Product | ​2.2 | 1
​12.2 | Marketing & Communications | Define soft-launch approach | Product | 8 | 8 | Not Started | On Track |  |  | Marketing | ​12.1 | 1
​12.3 | Marketing & Communications | Define full-launch approach | Marketing | 8 | 8 | Not Started | On Track |  |  |  | ​12.1 | 1
​12.4 | Marketing & Communications | Determine customer segments | Marketing | 9 | 9 | Not Started | On Track |  |  | Data | ​2.3 | 1
​12.5 | Marketing & Communications | Create OLB promotional content | Marketing | 9 | 9 | Not Started | On Track |  |  | Content | ​5.13 | 1
​12.6 | Marketing & Communications | Create mobile promotional content | Marketing | 9 | 9 | Not Started | On Track |  |  | Content | ​5.13 | 1
​12.7 | Marketing & Communications | Create email campaign | Marketing | 10 | 10 | Not Started | On Track |  |  |  | ​12.1 | 1
​12.8 | Marketing & Communications | Create website/intranet content | Marketing | 10 | 10 | Not Started | On Track |  |  |  | ​12.1 | 1
​12.9 | Marketing & Communications | Create employee communications | Internal Comms | 10 | 10 | Not Started | On Track |  |  |  | ​12.1 | 1
​12.10 | Marketing & Communications | Compliance review | Compliance | 11 | 11 | Not Started | On Track |  |  |  | ​12.5–12.9 | 1
​12.11 | Marketing & Communications | Revise materials | Marketing | 11 | 11 | Not Started | On Track |  |  |  | ​12.10 | 1
​12.12 | Marketing & Communications | Final marketing approval | Marketing | 12 | 12 | Not Started | On Track |  |  | Compliance | ​12.11 | 1 | Milestone
​12.13 | Marketing & Communications | Schedule launch communications | Marketing | 13 | 13 | Not Started | On Track |  |  |  | ​12.12 | 1
​13.1 | Analytics & Measurement | Define measurement framework | Product | 6 | 6 | Not Started | On Track |  |  | Data | ​2.12 | 1
​13.2 | Analytics & Measurement | Define enrollment metric | Data | 6 | 6 | Not Started | On Track |  |  |  | ​13.1 | 1
​13.3 | Analytics & Measurement | Define active usage metric | Data | 6 | 6 | Not Started | On Track |  |  |  | ​13.1 | 1
​13.4 | Analytics & Measurement | Define navigation click-through | Data | 6 | 6 | Not Started | On Track |  |  |  | ​13.1 | 1
​13.5 | Analytics & Measurement | Define SSO failure metric | Data | 6 | 6 | Not Started | On Track |  |  | Tech | ​13.1 | 1
​13.6 | Analytics & Measurement | Define support-contact metric | Ops | 7 | 7 | Not Started | On Track |  |  | Data | ​13.1 | 1
​13.7 | Analytics & Measurement | Establish baseline | Data | 7 | 7 | Not Started | On Track |  |  |  | ​13.1–13.6 | 1
​13.8 | Analytics & Measurement | Implement tracking | Tech | 8 | 8 | Not Started | On Track |  |  | Data | ​8.12 | 1
​13.9 | Analytics & Measurement | Validate tracking in test | QA | 9 | 9 | Not Started | On Track |  |  | Data | ​9.15 | 1
​13.10 | Analytics & Measurement | Build launch dashboard | Data | 11 | 11 | Not Started | On Track |  |  |  | ​13.8 | 1
​13.11 | Analytics & Measurement | Define launch reporting cadence | Product | 12 | 12 | Not Started | On Track |  |  | Data | ​13.10 | 1
​14.1 | Production Readiness | Complete production change request | Tech | 11 | 11 | Not Started | On Track |  |  | PM | ​9.19 | 1
​14.2 | Production Readiness | Confirm production configuration | Fiserv | 11 | 11 | Not Started | On Track |  |  | SavvyMoney | ​8.16 | 1
​14.3 | Production Readiness | Confirm production URLs | Tech | 11 | 11 | Not Started | On Track |  |  |  | ​14.2 | 1
​14.4 | Production Readiness | Confirm production SSO | Tech | 11 | 11 | Not Started | On Track |  |  | Vendor | ​14.2 | 1
​14.5 | Production Readiness | Confirm production entitlements | Fiserv | 11 | 11 | Not Started | On Track |  |  |  | ​14.2 | 1
​14.6 | Production Readiness | Confirm production monitoring | Tech | 12 | 12 | Not Started | On Track |  |  |  | ​13.10 | 1
​14.7 | Production Readiness | Final security approval | Security | 12 | 12 | Not Started | On Track |  |  |  | ​7.9 | 1
​14.8 | Production Readiness | Final compliance approval | Compliance | 12 | 12 | Not Started | On Track |  |  |  | ​6.13 | 1
​14.9 | Production Readiness | Final UAT approval | Product | 11 | 11 | Not Started | On Track |  |  |  | ​10.13 | 1
​14.10 | Production Readiness | Operational readiness approval | Operations | 12 | 12 | Not Started | On Track |  |  |  | ​11.14 | 1
​14.11 | Production Readiness | Marketing readiness approval | Marketing | 12 | 12 | Not Started | On Track |  |  |  | ​12.12 | 1
​14.12 | Production Readiness | Prepare rollback plan | Tech | 12 | 12 | Not Started | On Track |  |  |  | ​14.2 | 1
​14.13 | Production Readiness | Prepare production validation script | QA | 12 | 12 | Not Started | On Track |  |  |  | ​14.2 | 1
​14.14 | Production Readiness | Conduct Go/No-Go meeting | Sponsor | 13 | 13 | Not Started | On Track |  |  | PM | ​14.1–14.13 | 1 | Milestone
​15.1 | Production Deployment | Deploy/configure production | Fiserv | 13 | 13 | Not Started | On Track |  |  | SavvyMoney | ​14.14 | 1 | Milestone
​15.2 | Production Deployment | Enable OLB integration | Fiserv | 13 | 13 | Not Started | On Track |  |  |  | ​15.1 | 1
​15.3 | Production Deployment | Enable mobile integration | Fiserv | 13 | 13 | Not Started | On Track |  |  |  | ​15.1 | 1
​15.4 | Production Deployment | Production smoke test | QA | 13 | 13 | Not Started | On Track |  |  |  | ​15.1–15.3 | 1
​15.5 | Production Deployment | Validate SSO | QA | 13 | 13 | Not Started | On Track |  |  | Tech | ​15.4 | 1
​15.6 | Production Deployment | Validate enrollment | Product | 13 | 13 | Not Started | On Track |  |  | QA | ​15.4 | 1
​15.7 | Production Deployment | Validate analytics | Data | 13 | 13 | Not Started | On Track |  |  |  | ​15.4 | 1
​15.8 | Production Deployment | Confirm no critical defects | PM | 13 | 13 | Not Started | On Track |  |  | QA | ​15.4–15.7 | 1
​15.9 | Production Deployment | Production acceptance | Product | 13 | 13 | Not Started | On Track |  |  |  | ​15.8 | 1 | Milestone
​16.1 | Soft Launch | Make capability available | Product | 13 | 13 | Not Started | On Track |  |  | Tech | ​15.9 | 1 | Milestone
​16.2 | Soft Launch | Hold broad customer marketing | Marketing | 13 | 13 | Not Started | On Track |  |  |  | ​16.1 | 1
​16.3 | Soft Launch | Monitor enrollment | Product | 13 | 14 | Not Started | On Track |  |  | Data | ​16.1 | 2
​16.4 | Soft Launch | Monitor authentication failures | Tech | 13 | 14 | Not Started | On Track |  |  |  | ​16.1 | 2
​16.5 | Soft Launch | Monitor support contacts | Operations | 13 | 14 | Not Started | On Track |  |  |  | ​16.1 | 2
​16.6 | Soft Launch | Monitor defects | QA | 13 | 14 | Not Started | On Track |  |  | Product | ​16.1 | 2
​16.7 | Soft Launch | Review customer feedback | Product | 14 | 14 | Not Started | On Track |  |  | UX | ​16.1 | 1
​16.8 | Soft Launch | Resolve launch issues | Tech | 14 | 14 | Not Started | On Track |  |  | Vendor | ​16.3–16.7 | 1
​16.9 | Soft Launch | Soft-launch health review | PM | 14 | 14 | Not Started | On Track |  |  | Product | ​16.3–16.8 | 1
​16.10 | Soft Launch | Approve broad marketing | Sponsor | 14 | 14 | Not Started | On Track |  |  | Product | ​16.9 | 1 | Milestone
​17.1 | General Launch | Activate OLB promotion | Marketing | 15 | 15 | Not Started | On Track |  |  | Digital | ​16.10 | 1 | Milestone
​17.2 | General Launch | Activate mobile promotion | Marketing | 15 | 15 | Not Started | On Track |  |  | Digital | ​16.10 | 1
​17.3 | General Launch | Send customer email | Marketing | 15 | 15 | Not Started | On Track |  |  |  | ​16.10 | 1
​17.4 | General Launch | Publish customer content | Marketing | 15 | 15 | Not Started | On Track |  |  |  | ​16.10 | 1
​17.5 | General Launch | Publish employee communication | Internal Comms | 15 | 15 | Not Started | On Track |  |  |  | ​16.10 | 1
​17.6 | General Launch | Begin launch reporting | Data | 15 | 15 | Not Started | On Track |  |  | Product | ​17.1–17.5 | 1
​18.1 | Hypercare / Stabilization | Daily launch-health review | PM | 15 | 15 | Not Started | On Track |  |  | Product | ​17.1 | 1
​18.2 | Hypercare / Stabilization | Monitor SSO success rate | Tech | 15 | 17 | Not Started | On Track |  |  | Data | ​17.1 | 3
​18.3 | Hypercare / Stabilization | Monitor enrollment | Product | 15 | 17 | Not Started | On Track |  |  | Data | ​17.1 | 3
​18.4 | Hypercare / Stabilization | Monitor engagement | Product | 15 | 17 | Not Started | On Track |  |  | Data | ​17.1 | 3
​18.5 | Hypercare / Stabilization | Monitor support volume | Operations | 15 | 17 | Not Started | On Track |  |  |  | ​17.1 | 3
​18.6 | Hypercare / Stabilization | Prioritize production defects | Product | 15 | 17 | Not Started | On Track |  |  | Tech | ​17.1 | 3
​18.7 | Hypercare / Stabilization | Resolve priority issues | Tech | 15 | 17 | Not Started | On Track |  |  | Vendor | ​18.6 | 3
​18.8 | Hypercare / Stabilization | Review early customer feedback | Product | 16 | 16 | Not Started | On Track |  |  | UX | ​17.1 | 1
​18.9 | Hypercare / Stabilization | 30-day performance review | Product |  |  | Not Started | Schedule TBD |  |  | Data | ​17.1 |  |  | Timing is listed as post-launch in the source schedule. Assign a project week when governance confirms the review date.
​18.10 | Hypercare / Stabilization | Transition to BAU support | PM | 17 | 17 | Not Started | On Track |  |  | Ops | ​Stable production | 1 | Milestone
​18.11 | Hypercare / Stabilization | Capture lessons learned | PM | 17 | 17 | Not Started | On Track |  |  |  | ​18.10 | 1
​18.12 | Hypercare / Stabilization | Close project | Sponsor | 17 | 17 | Not Started | On Track |  |  | PM | ​18.11 | 1 | Milestone
​G1 | Stage Gates | G1 Scope Approved | Sponsor | 3 | 3 | Not Started | Due Soon |  |  | Product | ​2.14 | 1 | Stage Gate | Scope, capabilities, owners, and business objectives approved | 70
​G2 | Stage Gates | G2 Solution Approved | Architecture | 5 | 5 | Not Started | On Track |  |  | Product | ​4.17, 5.13 | 1 | Stage Gate | Architecture, SSO, data flow, and UX approved
​G3 | Stage Gates | G3 Risk Approved | Legal | 6 | 6 | Not Started | On Track |  |  | Compliance; Security | ​3.8, 6.13, 7.9 | 1 | Stage Gate | Vendor risk, privacy, legal, compliance, and security approvals complete
​G4 | Stage Gates | G4 Build Complete | PM | 8 | 8 | Not Started | On Track |  |  | Tech | ​8.16 | 1 | Stage Gate | Configuration and integration complete in test
​G5 | Stage Gates | G5 QA Complete | QA | 10 | 10 | Not Started | On Track |  |  |  | ​9.19 | 1 | Stage Gate | System, mobile, browser, accessibility, analytics, and regression testing passed
​G6 | Stage Gates | G6 UAT Complete | Product | 11 | 11 | Not Started | On Track |  |  |  | ​10.13 | 1 | Stage Gate | Business acceptance obtained and critical defects resolved
​G7 | Stage Gates | G7 Launch Ready | Sponsor | 13 | 13 | Not Started | On Track |  |  | PM | ​14.14 | 1 | Stage Gate | Operations, support, analytics, marketing, monitoring, and rollback ready
​G8 | Stage Gates | G8 Production Accepted | Product | 13 | 13 | Not Started | On Track |  |  |  | ​15.9 | 1 | Stage Gate | Production smoke testing and acceptance complete
​G9 | Stage Gates | G9 Market Ready | Sponsor | 14 | 14 | Not Started | On Track |  |  | Product | ​16.10 | 1 | Stage Gate | Soft launch stable enough to begin broad promotion
​G10 | Stage Gates | G10 BAU | Sponsor | 17 | 17 | Not Started | On Track |  |  | PM | ​18.10 | 1 | Stage Gate | Hypercare complete and ownership transitioned to business-as-usual support

## Milestones & Gates
Milestones & Stage Gates
Linked to the Master Plan; use Not Needed only when governance removes an event
WBS / Gate ID | Type | Event | Target Week | Accountable Owner | Status | Exit Criteria / Deliverable
​1.20 | Milestone | Kickoff | 2 | PM | Not Started | Project team, governance, and working cadence established
​2.14 | Milestone | Requirements complete | 3 | Product | Not Started | Product requirements and success measures finalized
​G1 | Stage Gate | Scope Approved | 3 | Sponsor | Not Started | Scope, capabilities, owners, and business objectives approved
​4.17 | Milestone | Technical design approved | 4 | Client | Not Started | Integration design and environment approach approved
​5.13 | Milestone | UX approved | 5 | Product | Not Started | Web, mobile, consent, error, and support experience approved
​G2 | Stage Gate | Solution Approved | 5 | Architecture | Not Started | Architecture, SSO, data flow, and UX approved
​6.13 | Milestone | Legal and compliance approved | 6 | Legal | Not Started | Required legal, privacy, consent, and disclosure conditions cleared
​7.9 | Milestone | Security approved | 6 | Security | Not Started | Security findings resolved and approval recorded
​G3 | Stage Gate | Risk Approved | 6 | Legal | Not Started | Vendor risk, privacy, legal, compliance, and security approvals complete
​8.16 | Milestone | Integration complete | 8 | PM | Not Started | Working integration and configuration complete in test
​G4 | Stage Gate | Build Complete | 8 | PM | Not Started | Configuration and integration complete in test
​9.19 | Milestone | QA complete | 10 | QA | Not Started | System and regression testing passed
​G5 | Stage Gate | QA Complete | 10 | QA | Not Started | System, mobile, browser, accessibility, analytics, and regression testing passed
​10.13 | Milestone | UAT complete | 11 | Product | Not Started | Business acceptance obtained
​G6 | Stage Gate | UAT Complete | 11 | Product | Not Started | Business acceptance obtained and critical defects resolved
​11.14 | Milestone | Operational readiness complete | 12 | PM | Not Started | Support, documentation, training, and escalation paths ready
​12.12 | Milestone | Marketing approved | 12 | Marketing | Not Started | Launch communications approved
​14.14 | Milestone | Go/No-Go | 13 | Sponsor | Not Started | Cross-functional production launch decision recorded
​15.1 | Milestone | Production deployment | 13 | Fiserv | Not Started | Production configuration deployed
​15.9 | Milestone | Production accepted | 13 | Product | Not Started | Production validation completed without critical defects
​16.1 | Milestone | Soft launch | 13 | Product | Not Started | Capability available with broad marketing held
​G7 | Stage Gate | Launch Ready | 13 | Sponsor | Not Started | Operations, support, analytics, marketing, monitoring, and rollback ready
​G8 | Stage Gate | Production Accepted | 13 | Product | Not Started | Production smoke testing and acceptance complete
​16.10 | Milestone | Market ready | 14 | Sponsor | Not Started | Soft-launch health supports broad promotion
​G9 | Stage Gate | Market Ready | 14 | Sponsor | Not Started | Soft launch stable enough to begin broad promotion
​17.1 | Milestone | General launch | 15 | Marketing | Not Started | OLB promotion activated
​18.10 | Milestone | BAU transition | 17 | PM | Not Started | Ongoing ownership transferred to operations
​18.12 | Milestone | Project close | 17 | Sponsor | Not Started | Lessons learned captured and project closure approved
​G10 | Stage Gate | BAU | 17 | Sponsor | Not Started | Hypercare complete and ownership transitioned to business-as-usual support

## Timeline
Implementation Timeline
Gantt-style view by relative project week
Delivery Stage | Start | End | Primary Focus | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Define | 1 | 5 | Scope, product, vendors, technical design, UX, and risk review
Build | 5 | 8 | Fiserv and SavvyMoney configuration, SSO, navigation, and analytics
Prove | 7 | 11 | QA, UAT, accessibility, security validation, and defects
Prepare | 8 | 13 | Operations, support, training, communications, and release approvals
Release | 13 | 17 | Production, soft launch, general launch, and hypercare
Detailed workstreams
Phase / Workstream | Start | End | Exit / Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project Initiation | 1 | 2 | Charter, governance, team, and kickoff complete
Business & Product Definition | 1 | 3 | Product scope, customer experience, and requirements approved
Vendor / Contract Readiness | 1 | 4 | Commercial, support, and risk dependencies resolved
Technical Discovery | 2 | 4 | Integration, SSO, data flow, environments, and solution design approved
UX / Experience Design | 2 | 5 | Web, mobile, consent, support, and accessibility experience approved
Legal / Compliance / Privacy | 2 | 6 | Legal, compliance, privacy, and disclosure requirements approved
Security / Risk | 4 | 6 | Security findings resolved and approval obtained
Configuration / Development | 5 | 8 | Working test integration and supporting configuration complete
QA / System Testing | 7 | 10 | System, mobile, browser, accessibility, analytics, and regression testing passed
User Acceptance Testing | 9 | 11 | Business acceptance obtained and critical defects resolved
Operations & Support Readiness | 8 | 12 | Support model, documentation, training, and escalation paths ready
Marketing & Communications | 8 | 13 | Launch communications approved and scheduled
Analytics & Measurement | 6 | 12 | Launch metrics, tracking, dashboard, and reporting cadence ready
Production Readiness | 11 | 13 | Production, rollback, monitoring, and cross-functional approvals ready
Production Deployment | 13 | 13 | Production integration validated and accepted
Soft Launch | 13 | 14 | Production stability confirmed and broad marketing approved
General Launch | 15 | 15 | Customer and employee launch communications activated
Hypercare / Stabilization | 15 | 17 | Production stabilized, ownership transitioned, and project closed
Stage gates
Gate | Target | Owner | Approval Criteria | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
​G1 | 3 | Sponsor | Scope, capabilities, owners, and business objectives approved | 3: ​G1
​G2 | 5 | Architecture | Architecture, SSO, data flow, and UX approved | 5: ​G2
​G3 | 6 | Legal | Vendor risk, privacy, legal, compliance, and security approvals complete | 6: ​G3
​G4 | 8 | PM | Configuration and integration complete in test | 8: ​G4
​G5 | 10 | QA | System, mobile, browser, accessibility, analytics, and regression testing passed | 10: ​G5
​G6 | 11 | Product | Business acceptance obtained and critical defects resolved | 11: ​G6
​G7 | 13 | Sponsor | Operations, support, analytics, marketing, monitoring, and rollback ready | 13: ​G7
​G8 | 13 | Product | Production smoke testing and acceptance complete | 13: ​G8
​G9 | 14 | Sponsor | Soft launch stable enough to begin broad promotion | 14: ​G9
​G10 | 17 | Sponsor | Hypercare complete and ownership transitioned to business-as-usual support | 17: ​G10