# Credit Sense and Fiserv OLB Team Project Plan

Condensed Client Delivery Plan Organized by Team

This working plan consolidates the 231-line implementation checklist into outcome-based work items for integrating Credit Sense by SavvyMoney into Fiserv Online Banking. Five checkpoints give leadership a simple view of progress, while completion criteria preserve the major delivery requirements under the team responsible for each outcome.

| Project Profile | Current Baseline |
| --- | --- |
| Client |  |
| Digital Lead |  |
| Planning Horizon | 19 project weeks |
| Release 1 Readiness Cutoff | Friday, October 2, 2026 |
| Release 1 Target | October 5, 2026 |
| Teams | 9 |
| Key Checkpoints | 5 |
| Managed Work Items | 62 |
| Overall Status | Not Started |

Planning basis  All Release 1 readiness work must be complete by Friday, October 2, 2026. Monday, October 5 is reserved for production activation and validation. Post-release monitoring and Release 2 planning are tracked separately in Weeks 17 through 19.

# Using This Project Plan

Leadership reviews the five checkpoints. Each team maintains its outcome-based work items, and Digital coordinates dependencies that cross team boundaries. Smaller implementation steps are captured under Complete When so they remain visible without becoming separate rows.

# Weekly Maintenance

Before the weekly meeting, each team updates task status, blocked by, and next action.

During the meeting, review the Next Two Weeks register and address blocked or at risk work first.

After the meeting, record decisions, scope changes, and checkpoint results in the project controls section.

Treat October 2 as the hard Release 1 readiness cutoff; October 5 contains only production activation and validation work.

# Not Needed Tasks

Use Not Needed when a work item does not apply to the client. Record the reason in the weekly register or project controls, then remove that row from the client working copy so it no longer appears. Keep an unchanged baseline copy for traceability. Word does not automatically filter table rows when a status changes, so this baseline and working-copy method is the reliable way to remove excluded work.

# Team Organization

The schedule is organized in this working order: Digital, Product, Marketing, Technology, Vendor, Data and Analytics, QA, Customer Support, and Corporate Training.

Vendor includes Fiserv and SavvyMoney. Specialist reviewers such as Security, Legal, Privacy, and Compliance remain identified as lead roles or partners within the applicable team activity.

# Status Definitions

| Status | When To Use It |
| --- | --- |
| Not Started | Work has not begun. |
| In Progress | Work is underway with an accountable owner. |
| At Risk | The target or exit criteria may be missed. Mitigation is required. |
| Blocked | Work cannot proceed until a decision or action occurs. |
| Complete | The deliverable is accepted and the dependency is satisfied. |
| Not Needed | The task does not apply to this client and is removed from the working copy. |

# Key Checkpoints

A checkpoint summarizes an outcome; it does not replace the underlying team activities. Mark it complete only when the stated result is true.

| ID | Checkpoint | Target | Lead Team | Complete When | Status |
| --- | --- | --- | --- | --- | --- |
| CP1 | Solution Confirmed | Week 6 | Product | Scope, customer experience, technical solution, data requirements, vendor responsibilities, and required security, legal, privacy, and compliance reviews are confirmed. | Not Started |
| CP2 | Configurations Complete | Week 8 | Technology | Test environments, single sign on, navigation, entitlements, branding, customer-data mapping, analytics tagging, monitoring, and initial integration testing are complete. | Not Started |
| CP3 | Ready for Production | Oct 2, 2026 (W16) | Digital | Functional QA, broader end-to-end UAT, critical defect resolution, final approvals, production and rollback plans, customer support, training, communications, analytics, and the Go or No Go review are complete by Friday, October 2. | Not Started |
| CP4 | Release 1 Complete | Oct 5, 2026 (W17) | Digital | Production activation and validation succeed on Monday, October 5, customer access and launch communications are live, and no critical launch issue remains open. | Not Started |
| CP5 | Release 2 Planning | Oct 23, 2026 (W19) | Product | Release 1 results and feedback are reviewed, Release 2 scope is prioritized, delivery dependencies and training impacts are understood, and owners and target timing are confirmed. | Not Started |

# Delivery Roadmap

Blue cells show the planned work window for each checkpoint. The checkpoint target appears in the first column.

| Checkpoint and Target | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CP1 Solution Confirmed Week 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CP2 Configurations Complete Week 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CP3 Ready for Production Oct 2, 2026 (W16) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CP4 Release 1 Complete Oct 5, 2026 (W17) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CP5 Release 2 Planning Oct 23, 2026 (W19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Team and Checkpoint Map

Lead identifies the team responsible for confirming the checkpoint. Support identifies teams with required activities or evidence.

| Team | CP1 Solution Confirmed | CP2 Configurations Complete | CP3 Ready for Production | CP4 Release 1 Complete | CP5 Release 2 Planning |
| --- | --- | --- | --- | --- | --- |
| Digital | Support | Support | Lead | Lead | Support |
| Product | Lead | Support | Support | Support | Lead |
| Marketing | Support | Support | Support | Support | Support |
| Technology | Support | Lead | Support | Support | Support |
| Vendor | Support | Support | Support | Support | Support |
| Data/Analytics | Support | Support | Support | Support | Support |
| QA |  |  | Support |  |  |
| Customer Support | Support |  | Support | Support | Support |
| Corporate Training |  |  | Support |  | Support |

# Next Two Weeks

Use this short register during the weekly meeting. Include only work that is active, starting soon, at risk, or blocked. Complete and Not Needed activities do not appear here.

| Team | ID | Activity | Owner | Status | Next Action | Blocker or Decision Needed |
| --- | --- | --- | --- | --- | --- | --- |

# Detailed Team Schedule

Work items are grouped by accountable team. Update Status here, and use the Next Two Weeks register for active next actions and blockers. The Complete When column carries the major checklist coverage that was consolidated from the detailed source plan.

## Digital

Primary focus  Program coordination, digital-channel decisions, governance, dependencies, release management, and project closure.

Weeks 1 through 19   8 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D.1 | Establish sponsorship, governance, and delivery team | Digital Lead | All Teams | CP1 | Jun 19 | Not Started | Sponsor, PM, team leads, vendor contacts, meeting cadence, decision log, and RAID process are confirmed. |
| D.2 | Approve the Release 1 scope and schedule baseline | Digital Lead | Product; Vendor | CP1 | Jun 26 | Not Started | In-scope outcomes, exclusions, launch approach, checkpoints, owners, and October 5 target are approved. |
| D.3 | Manage risks, decisions, dependencies, and status | Project Manager | All Teams | CP3 | Oct 2 | Not Started | Cross-team risks and decisions are current; unresolved items have an owner, action, and due date. |
| D.4 | Build the integrated readiness and cutover plan | Project Manager | Technology; Vendor; Product | CP3 | Sep 25 | Not Started | Cutover sequence, communications, validation, support, rollback, and command-center responsibilities are documented. |
| D.5 | Complete the final Go or No Go review | Sponsor | All Teams | CP3 | Oct 2 | Not Started | Every Release 1 readiness work item is complete or formally accepted, with approval recorded by Friday, October 2. |
| D.6 | Coordinate Release 1 activation | Digital Lead | Technology; Vendor; Product | CP4 | Oct 5 | Not Started | Production activation and validation complete on October 5, with executive status and issue ownership communicated. |
| D.7 | Close Release 1 and transition to business as usual | Project Manager | Customer Support; Product | CP4 | Oct 16 | Not Started | Launch issues are resolved or transferred, support ownership is accepted, and lessons learned are captured. |
| D.8 | Confirm the Release 2 planning process and owners | Digital Lead | Product; All Teams | CP5 | Oct 23 | Not Started | Release 2 planning owners, decision process, dependencies, and target timing are documented. |

## Product

Primary focus  Scope, requirements, customer experience, business acceptance, launch health, and the Release 2 roadmap.

Weeks 1 through 19   10 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P.1 | Define Release 1 capabilities, exclusions, and target customers | Product Lead | Digital; Marketing | CP1 | Jun 26 | Not Started | First-release capabilities, eligibility, value proposition, customer segments, and out-of-scope items are approved. |
| P.2 | Approve the web and mobile customer journeys | Product Lead | Digital; Technology | CP1 | Jul 10 | Not Started | OLB and mobile entry points, navigation, enrollment, returning-user experience, and responsive behavior are approved. |
| P.3 | Approve consent, disclosure, error, and support experiences | Product Lead | Compliance; Customer Support | CP1 | Jul 17 | Not Started | Consent and disclosure placement, terms, error states, support links, and escalation experience are approved. |
| P.4 | Complete legal, compliance, and privacy approval | Compliance Lead | Legal; Privacy; Marketing | CP1 | Jul 24 | Not Started | Required legal, FCRA, Reg V, privacy, terms, disclosures, consent, and marketing-claim reviews are complete. |
| P.5 | Define UAT participants, scenarios, and acceptance criteria | Product Lead | Business Users; Customer Support | CP3 | Aug 21 | Not Started | UAT covers complete customer and employee journeys, operational handling, content, devices, browsers, and accessibility. |
| P.6 | Prepare UAT users, accounts, instructions, and environment | Product Lead | Technology; Vendor | CP3 | Sep 4 | Not Started | Participants can access the environment, test accounts and data are ready, and scripts and issue logging are understood. |
| P.7 | Execute end-to-end UAT | UAT Lead | Business Users; Support; Marketing | CP3 | Sep 18 | Not Started | Business users validate web and mobile journeys, browsers, accessibility, content, support paths, analytics, and failure handling. |
| P.8 | Resolve UAT issues and obtain business signoff | Product Lead | Technology; Vendor | CP3 | Sep 25 | Not Started | Critical UAT issues are corrected and retested; remaining issues are accepted with owners and dates; signoff is recorded. |
| P.9 | Confirm product acceptance for Release 1 | Product Lead | Digital; Marketing | CP3 | Oct 2 | Not Started | Approved experience, capabilities, disclosures, content, and UAT results are ready for the October 5 launch. |
| P.10 | Prioritize Release 2 outcomes and scope | Product Lead | All Teams | CP5 | Oct 23 | Not Started | Release 1 feedback and results are reviewed and the Release 2 scope, measures, dependencies, and priorities are agreed. |

## Marketing

Primary focus  Launch strategy, promotional placement, customer and employee communications, campaign readiness, and market activation.

Weeks 4 through 19   7 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M.1 | Approve the launch communication and promotion strategy | Marketing Lead | Product; Compliance | CP1 | Jul 24 | Not Started | Audiences, channels, offers, promotional entry points, messaging, claims, and approval path are confirmed. |
| M.2 | Create and approve OLB and mobile promotional content | Marketing Lead | Product; Compliance | CP3 | Sep 4 | Not Started | OLB and mobile placements, copy, creative, calls to action, and required disclosures are approved. |
| M.3 | Create and approve customer email and web content | Marketing Lead | Product; Compliance | CP3 | Sep 11 | Not Started | Customer email, website or intranet content, FAQs, links, and legal language are final. |
| M.4 | Prepare employee and internal communications | Internal Communications | Customer Support; Corporate Training | CP3 | Sep 11 | Not Started | Employee messaging, launch guidance, escalation contacts, and timing are approved. |
| M.5 | Schedule and validate all Release 1 communications | Marketing Lead | Digital; Technology | CP3 | Oct 2 | Not Started | Every launch communication and promotion is scheduled, links are tested, owners are confirmed, and final approval is recorded by October 2. |
| M.6 | Activate and verify launch communications | Marketing Lead | Digital | CP4 | Oct 5 | Not Started | Approved OLB, mobile, email, web, and employee communications activate on October 5 and are verified. |
| M.7 | Identify Release 2 communication needs | Marketing Lead | Product | CP5 | Oct 23 | Not Started | Release 2 audience, channel, content, compliance, and lead-time considerations are documented. |

## Technology

Primary focus  Architecture, security, environments, single sign on, integration, configuration, monitoring, and production deployment.

Weeks 2 through 19   10 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T.1 | Document the current Fiserv OLB technical environment | Technology Lead | Vendor | CP1 | Jul 3 | Not Started | OLB version, web and mobile architecture, environments, URLs, authentication, customer identifiers, and constraints are documented. |
| T.2 | Approve the integration, SSO, mobile, and data-flow design | Architecture Lead | Vendor; Product | CP1 | Jul 10 | Not Started | Integration method, SSO, enrollment, mobile, data transmission, error handling, and support flows are approved. |
| T.4 | Confirm test and production environments | Technology Lead | Vendor | CP1 | Jul 24 | Not Started | Environment access, URLs, versions, credentials, production monitoring, and support contacts are confirmed. |
| T.3 | Complete architecture, security, and privacy reviews | Security Lead | Privacy; Vendor | CP1 | Jul 24 | Not Started | Encryption, storage, retention, vendor controls, logging, monitoring, and security findings are approved or resolved. |
| T.5 | Configure the client integration and digital entry points | Technology Lead | Vendor; Product | CP2 | Aug 7 | Not Started | SSO, OLB and mobile navigation, entitlements, enrollment, disclosures, branding, and support links are configured. |
| T.6 | Configure monitoring, logging, analytics hooks, and alerts | Technology Lead | Data/Analytics; Vendor | CP2 | Aug 7 | Not Started | Production-ready logs, alerts, dashboards, event tracking, and escalation thresholds are configured. |
| T.7 | Resolve functional QA and UAT defects | Technology Lead | Vendor; QA; Product | CP3 | Sep 25 | Not Started | Technology defects are triaged, corrected, deployed, and made available for functional QA or UAT retest. |
| T.8 | Approve production change, cutover, rollback, and validation plans | Technology Lead | Digital; Vendor; Product | CP3 | Oct 2 | Not Started | Production configuration, change approval, runbook, rollback steps, validation script, and support coverage are complete by October 2. |
| T.9 | Deploy and validate the production integration | Technology Lead | Vendor; Product | CP4 | Oct 5 | Not Started | Production deployment, SSO, entry points, entitlements, monitoring, and smoke validation succeed on October 5. |
| T.10 | Assess Release 2 architecture and delivery dependencies | Architecture Lead | Vendor; Product | CP5 | Oct 23 | Not Started | Release 2 technical changes, estimates, risks, environments, security needs, and sequencing are documented. |

## Vendor

Primary focus  Fiserv and SavvyMoney contracting, configuration, dependencies, service commitments, testing support, and delivery estimates.

Weeks 1 through 19   9 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| V.1 | Confirm Fiserv and SavvyMoney delivery contacts and roles | Vendor Lead | Digital | CP1 | Jun 19 | Not Started | Implementation, technical, testing, production, and support contacts and responsibilities are confirmed. |
| V.2 | Complete contract, licensing, fees, SLA, and vendor-risk review | Vendor Manager | Legal; Procurement | CP1 | Jul 10 | Not Started | Licensed capabilities, fees, service commitments, data responsibilities, and vendor-risk requirements are approved. |
| V.3 | Confirm the joint solution design and implementation plan | Vendor Lead | Technology; Product | CP1 | Jul 17 | Not Started | Fiserv and SavvyMoney agree on integration, SSO, environments, responsibilities, dependencies, and delivery dates. |
| V.4 | Provision and verify nonproduction environments | Vendor Lead | Technology | CP2 | Jul 17 | Not Started | Fiserv and SavvyMoney test configurations are accessible and support the approved solution design. |
| V.5 | Complete vendor configuration and integration support | Vendor Lead | Technology | CP2 | Aug 7 | Not Started | Vendor-side branding, SSO, enrollment, data mapping, navigation, entitlements, disclosures, and connectivity are complete. |
| V.6 | Support testing and resolve vendor defects | Vendor Lead | QA; Product; Technology | CP3 | Sep 25 | Not Started | Vendor defects from functional QA and UAT are resolved or formally accepted with owners and delivery dates. |
| V.7 | Confirm production configuration and support readiness | Vendor Lead | Technology; Customer Support | CP3 | Oct 2 | Not Started | Production settings, URLs, entitlements, contacts, escalation paths, monitoring, and launch coverage are confirmed by October 2. |
| V.8 | Enable and support the production launch | Vendor Lead | Technology; Digital | CP4 | Oct 5 | Not Started | Vendor production enablement and launch support are complete on October 5, with critical issues resolved or owned. |
| V.9 | Provide Release 2 capabilities, estimates, and lead times | Vendor Lead | Product; Technology | CP5 | Oct 23 | Not Started | Vendor feasibility, cost, estimates, dependencies, and lead times are documented for Release 2 decisions. |

## Data/Analytics

Primary focus  Customer data requirements, tracking, KPIs, dashboards, launch reporting, and Release 1 performance analysis.

Weeks 2 through 19   5 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Define Release 1 KPIs and baseline measures | Analytics Lead | Product | CP1 | Jul 24 | Not Started | Enrollment, active use, navigation, SSO success, support contact, and engagement measures and baselines are approved. |
| A.2 | Confirm customer data and analytics requirements | Data Lead | Technology; Vendor; Privacy | CP1 | Jul 24 | Not Started | Required customer attributes, data ownership, mapping, privacy controls, retention, and event definitions are approved. |
| A.3 | Configure and validate analytics tracking | Analytics Lead | Technology; Product | CP2 | Aug 7 | Not Started | Required events and attributes are captured accurately in test and reconcile to the approved measurement framework. |
| A.4 | Build and validate launch reporting | Analytics Lead | Product; Technology | CP3 | Sep 25 | Not Started | Launch dashboard, access, data refresh, thresholds, owners, and reporting cadence are tested and ready by September 25. |
| A.5 | Monitor Release 1 results and inform Release 2 | Analytics Lead | Product; Customer Support | CP5 | Oct 23 | Not Started | Early results, usage, failures, support demand, and customer feedback are summarized with Release 2 recommendations. |

## QA

Primary focus  Functional test planning, functional execution, defect retesting, regression, and functional signoff.

Weeks 6 through 12   5 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Q.1 | Define the functional QA plan and exit criteria | QA Lead | Product; Technology | CP3 | Jul 31 | Not Started | Functional cases, environments, data, severity rules, entry criteria, exit criteria, and defect workflow are approved. |
| Q.2 | Prepare functional test accounts and data | QA Lead | Technology; Vendor | CP3 | Jul 31 | Not Started | Test accounts and data support new and returning users, eligibility, entitlements, enrollment, and failure scenarios. |
| Q.3 | Execute functional QA | QA Lead | Technology; Vendor | CP3 | Aug 14 | Not Started | Core functions pass: SSO, enrollment, navigation, entitlements, customer-data mapping, disclosures, support links, and error handling. |
| Q.4 | Retest functional defects and complete regression | QA Lead | Technology; Vendor | CP3 | Aug 28 | Not Started | Corrected functional defects pass retest and affected core functions pass regression. |
| Q.5 | Provide functional QA signoff | QA Lead | Product | CP3 | Sep 4 | Not Started | No open critical functional defect remains and QA exit criteria are met before end-to-end UAT begins. |

## Customer Support

Primary focus  Support ownership, procedures, FAQs, escalation paths, operational readiness, monitoring, and business-as-usual handoff.

Weeks 5 through 18   5 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.1 | Define the support model, ownership, and escalation paths | Support Lead | Digital; Vendor | CP1 | Jul 24 | Not Started | Level 1 ownership, Digital and vendor escalation, contacts, hours, severity handling, and service commitments are confirmed. |
| S.2 | Prepare support procedures, scripts, FAQs, and job aids | Support Lead | Product; Corporate Training | CP3 | Sep 4 | Not Started | Known scenarios, call and branch scripts, FAQs, troubleshooting, escalation, and support documentation are approved. |
| S.3 | Validate support workflows through UAT | Support Lead | Product; Vendor | CP3 | Sep 18 | Not Started | Support staff successfully handle representative enrollment, access, data, error, and escalation scenarios during UAT. |
| S.4 | Confirm launch staffing and operational readiness | Support Lead | Digital; Vendor | CP3 | Oct 2 | Not Started | Staffing, contacts, scripts, job aids, escalation coverage, issue logging, and launch-day availability are confirmed by October 2. |
| S.5 | Provide launch support and transition to business as usual | Support Lead | Digital; Data/Analytics | CP4 | Oct 16 | Not Started | Launch issues and support volumes are monitored, escalations are managed, and ongoing support ownership is accepted. |

## Corporate Training

Primary focus  Training needs, materials, scheduling, delivery, completion tracking, job aids, and future-release impacts.

Weeks 8 through 16   3 work items

| ID | Work Item | Owner | Partners | CP | Due | Status | Complete When |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C.1 | Confirm training audiences, objectives, and delivery approach | Training Lead | Customer Support; Product | CP3 | Aug 21 | Not Started | Required audiences, skills, delivery methods, schedule, completion expectations, and owners are confirmed. |
| C.2 | Develop and approve training materials and job aids | Training Lead | Customer Support; Product | CP3 | Sep 4 | Not Started | Training content, demonstrations, support guidance, job aids, and final approvals are complete. |
| C.3 | Deliver training and confirm readiness | Training Lead | Customer Support; Marketing | CP3 | Oct 2 | Not Started | Required training is delivered, completion and follow-up are documented, and workforce readiness is confirmed by October 2. |

# Project Controls

Maintain only the items that require cross-team visibility, leadership action, or a documented change. Add rows as needed and retain the approved record through project closure.

## Items Requiring Attention

| ID | Type | Description or Decision | Owner | Due | Status | Resolution or Decision |
| --- | --- | --- | --- | --- | --- | --- |

## Scope Change Log

| ID | Date | Requested Change | Impact | Decision | Owner |
| --- | --- | --- | --- | --- | --- |