## Slide 1
HCD Strategy Workshops
Recap of the work to date, and an outline for the next three sessions
Grounding the Lending and Credit Cards roadmap in the customer

## Slide 2
Where we are
A capability roadmap, built from your team's input — recapped before we ground it in the customer.
The landscape
Initiatives defined across Lending and Credit Cards, each with a stated enterprise and customer outcome.
The foundations
Origination, servicing, and a unified customer view underlie most items and gate the order of work.
The draft sequence
Three dependency-driven waves, with BNPL held at its stated Q3/Q4 as a fixed anchor.
Open items
NC segment, Start Smart, campaign logic, and one illegible note remain unresolved.

## Slide 3
From capability list to customer-grounded strategy
The roadmap so far is derived inside-out from team input and ordered by dependency. These three sessions add the outside-in half — segments, journey, and customer value — and use it to validate and commit the sequence.
1
Frame
Who we serve, and what they are trying to accomplish across origination and servicing.
Leave with — Segments, personas, framed problem
→
2
Explore
The target-state journey, and where OLB integration, activation, and cross-sell attach.
Leave with — Journey map and How-Might-We set
→
3
Prioritize
& sequence
Customer value against dependency; validate and commit the waves.
Leave with — Committed, grounded roadmap

## Slide 4
Workshop 1 · Frame
Move from an inside-out capability list to a shared view of who we serve and what they are trying to accomplish.
1 / 3
Inputs — the initiative landscape and current-state notes (pre-read)
15m
Frame & align
Objectives; the capability landscape as raw material
25m
Stakeholder Mapping
Customers and the partner groups touching these journeys
35m
Segments & personas
Resolve the NC segment; jobs-to-be-done per segment
30m
Rose, Thorn, Bud
Current-state origination and servicing experience
15m
Synthesize
Confirm priority segments for the next session
You leave with
Defined customer segments, NC resolved
Priority personas with jobs-to-be-done
Current-state pain and opportunity inventory
A framed problem statement
Participants — Core product, UX, and delivery, plus representation from the lending and cards partner groups.

## Slide 5
Workshop 2 · Explore
Map the target-state journey and locate where the OLB origination and servicing work surfaces for the customer.
2 / 3
Inputs — Workshop 1 segments, personas, and current-state inventory
10m
Recap & orient
Priority segment and framed problem
45m
Experience Diagramming
Target-state journey: origination → activation → servicing
25m
Locate the moments
Integration, onboarding/activation, and cross-sell points
25m
Statement Starters
How-Might-We questions from the key pains
15m
Synthesize
Consolidate the map; rank the How-Might-We set
You leave with
Target-state journey across the portfolio
OLB integration points located in the journey
Activation and cross-sell moments, in context
A prioritized How-Might-We set
Participants — Same core group; add anyone owning the OLB origination and servicing integration.

## Slide 6
Workshop 3 · Prioritize & sequence
Prioritize by customer value against dependency, validate the wave sequence against the journey, and commit.
3 / 3
Inputs — initiative dependencies and draft sequence; Workshop 2 journey and How-Might-We set
10m
Recap & orient
The journey and the ranked opportunities
40m
Importance/Difficulty Matrix
Customer value against effort and dependency
35m
Sequence validation
Test the three waves against the journey; hold BNPL
20m
Open-items decisions
Start Smart, campaign logic, and the rest
15m
Commit
Agree the roadmap; assign owners and next steps
You leave with
Initiatives plotted by value vs. difficulty
The wave sequence validated against the journey
Open items decided and logged
A committed, dependency-aware roadmap with owners
Participants — Core group plus a decision-maker empowered to commit the sequence.

## Slide 7
What you have after three sessions
A customer-grounded view of the credit and loan portfolio — segments, journeys, and jobs.
The OLB origination, servicing, activation, and cross-sell points located within that journey.
Initiatives prioritized by customer value and validated against their dependencies.
A committed, sequenced roadmap with owners — and the open items decided, not deferred.
To run these
A short pre-read before each session
One consistent core group across all three
Partner-group reps for the journeys in scope
A decision-maker present for session 3
About a week between sessions to synthesize
Outline assumes three 2-hour sessions; adjust scope per session if the count or length differs.